## Risk Log
Project Name: | Contrast E-commerce Platform
National Center: | N/A
Project Manager Name: | Ameen Al-Rahma
Project Description: | Development of an online clothing store using Agile methodology.
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
R1 | Open | High | Medium | Yellow | Scope creep due to adding extra features such as wishlist, reviews, and multi-language during development | May delay project completion and affect delivery of core features | Project Scope | Increasing number of features in backlog | New feature requests during sprint | Mitigation | Use MoSCoW prioritisation and restrict scope to Must Have features | Move additional features to future development
R2 | Closed | Medium | High | Yellow | Task complexity in implementing product management and variants structure | Slows development progress in early stages | Development | Tasks taking longer than expected | Difficulty structuring product and variant logic | Mitigation | Break tasks into smaller subtasks and test incrementally | Allocate extra time and simplify implementation
R3 | Closed | Medium | Medium | Yellow | Development environment issues (XAMPP / Laravel setup) | Delays initial development setup | Technical Environment | Errors during setup and configuration | Misconfiguration of environment | Mitigation | Debug configuration issues and reinstall environment | Use alternative setup or documented configuration
R4 | Open | High | Medium | Yellow | Integration issues between cart and checkout systems | System features may not work together correctly | Integration | Cart and checkout not functioning correctly together | Combining multiple system components | Mitigation | Perform integration testing after each sprint using Zephyr | Rework integration logic and retest
R5 | Open | High | Low | Yellow | Risk of data loss during development | Loss of progress and system data | Data Management | Missing or corrupted data | System crash or accidental deletion | Mitigation | Use GitHub for version control and regular commits | Restore from previous versions or backups
R6 | Open | Medium | Medium | Yellow | Time constraint limiting completion of all planned features | Some features may not be delivered | Project Schedule | Incomplete features near deadline | Limited development time | Mitigation | Prioritise features using MoSCoW method | Deliver only core features and defer others
x